## Summary
| Current Score, % | Scrum Progress | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Current
Roles | 0
Product Owner | 0 | Roles | 15 | 28 | 29 | 30 | 31 | 35 | 39
Development Team | 0 | Events | 12 | 20 | 30 | 33 | 35 | 40 | 43
Scrum Master | 0 | Artifacts | 25 | 25 | 28 | 35 | 35 | 37 | 38
Events | 0 | MAX | 100 | 100 | 100 | 100 | 100 | 100 | 100
Sprint | 0
Sprint Planning | 0
Daily Scrum | 0
Sprint Review | 0
Sprint Retrospective | 0
Artifacts | 0
Product Backlog | 0
Sprint Backlog | 0
Increment | 0

## Scrum Roles
Role | Rules | Practices | Comments | Assessment | Score | Risks When Not TRUE
Product Owner | The Product Owner is responsible for maximizing the value of the product and the work of the Development Team. | PO is defining goals of the product and individual releases | Product Owner is one person. If some responsibilities are done by other persons, outside Scrum Team than consider FALSE to some items. Scrum allows PO to delegate some responsibilities to the Development Team. In this case it is OK to select TRUE | SELECT … | 0 | If NOT TRUE the Development Team has a risk to produce low value outcomes on their own
|  | PO is having a view or ownership of the budgets and understanding constraints (e.g. Budget) |  | SELECT … |  | If NOT TRUE it decreases PO ability to a be good decision maker on PB priorities which creates risks with customer expectations
|  | PO is managing expectations upwards and downwards |  | SELECT … |  | If Product Owner doesn't manage effectively expectations both on development and business side it create a risk to meet customer expectations
|  | PO is reviewing and approving PBI acceptance tests, acceptance criteria, sprint goal and other requirements |  | SELECT … |  | If Product Owner doesn't timely approve acceptance tests, acceptance criteria and other requirements it create a risk of reworks
|  | PO is owning product vision, strategy and roadmap |  | SELECT … |  | If NOT TRUE it create risk with priorities chaos in the Development Team
| The Product Owner is the sole person responsible for managing the Product Backlog. | The Product Owner is one person, not a committee |  | SELECT … | 0 | Rework, priority mess, delivery in time
|  | A change in priorities is driven by the Product Owner |  | SELECT … |  | Rework, priority mess, miscommunications and conflicts
|  | PO is ordering items in the Product Backlog and is able to explain stakeholders the rational behind it |  | SELECT … |  | Risks to fail business expectations
|  | PO is responsible to keep Product Backlog visible, transparent, and clear to all, and shows what the Scrum Team will work on next; |  | SELECT … |  | Non-transparent Product Backlog create risks of uncertainty and sub-optimal organizational decisions from business side, which is strongly affecting entire Development Team
|  | PO is ensuring that the Development Team understands items in the Product Backlog. |  | SELECT … |  | Reworks, broken communications, escalations and conflicts
| For the Product Owner to succeed, the entire organization must respect his or her decisions. | The Product Owner’s decisions are visible in the content and ordering of the Product Backlog | Consider FALSE to some items when someone else is trying to communicate with Dev Team on behalf of Product Owner which is decreasing PO authority to make priority decisions. | SELECT … | 0 | Conflicts between PO and Dev Team, scope creeping, increase work in process and overtimes
|  | PO is ensuring that no one is telling the Development Team to work from a different set of requirements |  | SELECT … |  | Conflicts between PO and Dev Team, scope creeping, increase work in process and overtimes
|  | The Development Team isn’t acting on what anyone else says |  | SELECT … |  | Broken trust between PO and Dev Team. Risk when PO micromanage the Dev Team
|  | PO is accepting or rejecting work results |  | SELECT … |  | Mistmatched business expectations
|  | PO is resolving priority conflicts |  | SELECT … |  | Risks with sustainability of the development
Development Team | The Development Team consists of professionals who do the work of delivering a potentially releasable Increment of “Done” product at the end of each Sprint. | Development Team is accountable for delivering the Increment. | Consider FALSE to some items when you see that the Scrum Team is not fully functional and depends on outside experts to deliver increment | SELECT … | 0 | Risks that outside experts cannot be commited to the Scrum Team whichis creating huge risks with trust, delivery and to meet expectation
|  | Development Team is cross-functional, with all of the skills as a team necessary to create a product Increment; |  | SELECT … |  | The lack of certain skills impact Dev Team motivation and adds uncertainty to delivery
|  | Accountability for delivering increment is belonging to the Development Team as a whole, not individual senior team members. |  | SELECT … |  | If NOT TRUE the Dev Team cannot demonstrate commitement and responsible behaviours
|  | There are no clear separation in titles. Everyone in the Development Team takes accountability to do the best they can, helping each other to achieve the best possible outcomes |  | SELECT … |  | If NOT TRUE it creates a risk of internal conflicts inside the Dev Team, risks with balacing resource and overtimes on certain experts
|  | Development Team is owning development process under Scrum framework and improving its own engineering practice (automation, design, architecture, documentation, etc) |  | SELECT … |  | If NOT TRUE it creates a risk that the Dev Team won't grow its own maturity level
| Development Teams are structured and empowered by the organization to organize and manage their own work | Development Team is self-organizing. No one (not even the Scrum Master) tells the Development Team how to turn Product Backlog into Increments of potentially releasable functionality; | Consider FALSE to some items when someone outside the Dev Team is managing their plans, tasks assignments, micromanage status during the day and applying other command and control practices | SELECT … | 0 | If NOT TRUE it create a risk of pseudo-team which is unable to work without management
|  | Development Team is having no sub-teams, regardless of particular domains that need to be addressed like testing or business analysis |  | SELECT … |  | If NOT TRUE it creates a risk to fail delivery due to conflicts between sub-groups
|  | Development Team size is not less than 3 and not more than 9 |  | SELECT … |  | If MORE than 9 it increase risk to effectively build healthy communications between team members, if LESS than 3 it create a risk to produce valuable requirements faster
|  | Development Team is owning application design and architecture |  | SELECT … |  | If NOT TRUE it creates many impediments to the Dev Team, delays in design and architecture decisions break sustainable development process, risks with overtimes
|  | Development Team is commiting to create and implement improvement plan |  | SELECT … |  | If NOT TRUE it creates a risk to produce low quality Increment and quality decreasing with each new Sprint
Scrum Master | The Scrum Master is responsible for ensuring Scrum is understood and enacted. | The Scrum Master is ensuring that the Scrum Team adheres to Scrum theory, practices, and rules | Consider FALSE to some items when there is no someone to be responsible for growing Scrum maturity | SELECT … | 0 | If NOT TRUE it creates a risk to have predictable development process
|  | The Scrum Master is coaching the Development Team in organizational environments in which Scrum is not yet fully adopted and understood. |  | SELECT … |  | If NOT TRUE it creates a risk to fail Dev Team expected performance
|  | The Scrum Master is ensuring the Product Owner knows how to arrange the Product Backlog to maximize value; |  | SELECT … |  | If NOT TRUE it creates a risk to fail Dev Team expected performance
|  | The Scrum Master is managing Scrum Team using servant leadership techniques. |  | SELECT … |  | NOT TRUE creates a risk of the Scrum adoption
|  | The Scrum Master is facilitating Scrum events as requested or needed. |  | SELECT … |  | NOT TRUE creates a risk of disorganised Dev Team, cancelled Scrum meetings and Scrum deterioration
| Removing impediments to the Development Team’s progress; | The Scrum Master is helping those outside the Scrum Team understand which of their interactions with the Scrum Team are helpful and which aren’t | Consider FALSE for some items when there is nobody responsible for removing impediments which are hindering to adopt Scrum at its fullness according to the Scrum Guide | SELECT … | 0 | NOT TRUE creates a risk of not solved issues in communications beween different parties
|  | The Scrum Master is helping everyone change interactions to maximize the value created by the Scrum Team |  | SELECT … |  | NOT TRUE creates a risk to follow sub-optimal practices which don't bring any value
|  | The Scrum Master is finding new techniques for effective Product Backlog management; |  | SELECT … |  | NOT TRUE creates a risk of the ineffective Product Backlog management
|  | The Scrum Master is coaching the organization (client\vendor) in its Scrum adoption; |  | SELECT … |  | NOT TRUE creates a risk with transparency
|  | The Scrum Master is causing change that increases the productivity of the Scrum Team; |  | SELECT … |  | NOT TRUE will create a risk of improper Scrum usage

## Scrum Events
Event | Rule | Practices | Comments | Assessment | Score | Risks When Not TRUE
Sprint | No changes made to Sprint Backlog that could endanger the Sprint Goal | Scrum Team (all memebers) is having ONE shared goal for the current Sprint | If first statement is false, then other criteria for this rule would be likely false | SELECT … | 0 | NOT TRUE reduces overall team effectiveness
|  | The Sprint Goal is expressing business value of the Increment |  | SELECT … |  | NOT TRUE creates uncertanties with Project estimates
|  | The DT is showing oppennes when PO makes changes to the scope (requirements) of the current Sprint aligned to the Sprint Goal |  | SELECT … |  | Decreased trust and relations with customers
|  | The PO is showing respect for the current Sprint Goal and doesn't disrupt Developmnt Team focus with other tasks which are not aligned to the Sprint Goal |  | SELECT … |  | Affects team productivity and adds uncertanties
|  | The DT is demonstrating courage to say NO when the changes to the scope and priorities of the current Sprint are not aligned to the Sprint Goal |  | SELECT … |  | Risks with overtimes, cutting quality and increasing technical debt
| Sprint is time-boxed of one month or less during which a “Done”, useable, and potentially releasable product Increment is created | The definition of "Done" (DoD ) of the Sprint is including all activities (development, testing, documentation) to create usable and potentially releasable product Increment |  | SELECT … | 0 | When NOT TRUE there is a risk to produce unpredictable results
|  | The Scrum Team is never extending the initially agreed time-box of the Sprint |  | SELECT … |  | NOT TRUE breaks sustainability, time management, team discipline and transparency
|  | The DT is always committing to do all activities to meet DoD within time-box of the Sprint |  | SELECT … |  | NOT TRUE causes internal conflicts, decreasing team morale
|  | The SM is always setting impediments removal as a first priority |  | SELECT … |  | Risks to have long lived unsolved team problems can turn out to fail customer service
|  | New Sprint is starting immediately after the conclusion of the previous Sprint |  | SELECT … |  | Break sustainability and predictability of the dev process
| Quality goals do not decrease | The Scrum Team is understanding the quality goals and it is documented within DoD | On the wall or WIKI | SELECT … | 0 | Risks to have increased tech debt and reduced performance
|  | The Product Owner and stakeholders are showing respect to the quality goals (DoD) and never trying to push DT to complete more features obove their normal capacity |  | SELECT … |  | Overtimes and qulaity shortcuts
|  | The DT is opnly discussing problems with quality and together with Product Owner are trying to find a solution without postponing it to the next Sprint |  | SELECT … |  | Accumulated defects will result in release slippage
|  | There are tools which are capturing relevant code quality and product quality metrics transparent to the entire organization. | Sonar, Automated Regression, xUnit | SELECT … |  | NOT TRUE creates uncontrollable risk to fail initial estimates
|  | The DT team is committing to inspect quality metrics and instantly adapt the quality | CI, code review, etc | SELECT … |  | NOT TRUE creates a risk to fail estimates
| Scope may be clarified and re-negotiated between the Product Owner and Development Team as more is learned. | The PO is committing to clarify questions as Development Team is discovering the unexpected variances |  | SELECT … | 0 | Wastes due to delays, ineffective time management
|  | There are no delays in clarification process between DT and PO and SM usually helps DT to make the clarification process time effective |  | SELECT … |  | NOT TRUE decreasing overall team prodcutivity
|  | When changing the the scope and re-negotiating, the PO is showing respect for the remaining DT remaining capacity for the rest of the Sprint |  | SELECT … |  | NOT TRUE creates a risk of overtimes and quality deterioration
|  | When DT is demonstrating slower progress of the Sprint Backlog tasks, the PO is open to reduce the scope of SB and has a courage to tell stakeholders "bad news" |  | SELECT … |  | NOT TRUE will reduce PO authority of being effective decision maker
|  | The PO is not trying to change the requirements of the current Sprint whitout letting know the entire DT first. |  | SELECT … |  | NOT TRUE will reduce transparency and creates dev team unsatisfaction
Sprint Planning | Sprint Planning takes place, the attendants understand its purpose and key rules | Every member of the Scrum Team is showing-up on the Sprint Planning, including PO (mandatory) and SM (if needed). Entire Scrum Team is demonstrating commitment to collaboratively create a plan for the next Sprint. | Participants | SELECT … | 0 | NOT TRUE creates a risk to fail Sprint Planning
|  | Sprint Planning is time-boxed to a maximum of eight hours for a one-month Sprint and 4 hours for a two-week Sprint. Entire Scrum Team respect this time-box | Duration | SELECT … |  | NOT TRUE creates a risk of ineffective Sprint Planning
|  | Every Sprint is starting from the Sprint Planning immediately after Sprint Retrospective whithout any delays | Timeline | SELECT … |  | NOT TRUE decreasing sustainability and increases wastes
|  | Every team member is open to proactively participate in the Sprint Planning Session (no complains) | Collaboration | SELECT … |  | Risks with re-work, repeating same information many times and other wastes
|  | The Development Team is inviting other people to attend Sprint Planning in order to provide technical or domain expertise, if needed. | External People | SELECT … |  | NOT TRUE creates a risk of ineffective planning
| Sprint Planning answers the following: What can be delivered in the Increment resulting from the upcoming Sprint? | The Product Owner agree with Development Team the objective that the Sprint should achieve and the Product Backlog items that, if completed in the Sprint, would achieve the Sprint Goal | Objective of the Sprint | SELECT … | 0 | Creates a risk with dev team focus and failed expectation by the end of the Sprint
|  | In the Sprint Planning meeting the Development Team can produce forecast for the Sprint (DoD, Sprint Backlog, Projected Capacity, Past Performance); | Inputs | SELECT … |  | NOT TRUE creates a risk of producing non-reliable plans
|  | Only Development Team decides the number of items selected from the Product Backlog for the Sprint | Forming Scope | SELECT … |  | Quality deterioration, technical debt and failed delivery
|  | The Development Team don't provide strong commitment on the scope, but provides a commitment to achieve the best they can given the agreed Sprint Goal (one sentense business objective) | Sprint Goal | SELECT … |  | Quality deterioration, technical debt and failed delivery
|  | The Development Team respect priorities set by Product Owner and make plan accordingly | Priorities | SELECT … |  | NOT TRUE creates a risk to work in overtimes
| Sprint Planning answers the following: How will the work needed to deliver the Increment be achieved? | All Development Team members discusses on the Sprint Planning intended system design and the work needed to convert the Product Backlog into a working product Increment. |  | SELECT … | 0 | Repeating information several time, non-reliable estimates
|  | The Development Team forecast what it believes it can do in the upcoming Sprint and includes just enough work to the Sprint Backlog | Avoid strong commitment | SELECT … |  | Increasing pushing behaviours from business side, increase micromanagemnt behaviours from PO
|  | The Development Team decompose planned work to units of one day or less |  | SELECT … |  | Risk to radically fail initial estimates, risks to implement more than it is required
|  | The Development Team self-organizes to undertake the work in the Sprint Backlog, both during Sprint Planning and as needed throughout the Sprint. No assignments. |  | SELECT … |  | Non-responsible team
|  | Not "Ready" PBIs are not included into the Sprint scope until analysis is Done |  | SELECT … |  | Re-work and failed expectations
| By the end of the Sprint Planning, the Development Team should be able to explain to the Product Owner and Scrum Master how it intends to work as a self-organizing team to accomplish the Sprint Goal and create the anticipated Increment. | Sprint Goal is clear and set by the Product Owner in agreement with Development Team |  | SELECT … | 0 | Re-work and failed expectations
|  | If the Development Team determines it has too much or too little work, it has a courage to renegotiate the selected Product Backlog items with the Product Owner. |  | SELECT … |  | Reduce transparency and trust
|  | The Product Owner is committed to clarify the selected Product Backlog items and make trade-offs. |  | SELECT … |  | Non-reliable Sprint plan
|  | Sprint Backlog is created by the end of the Sprint Planning |  | SELECT … |  | Failed Sprint
|  | The Development Team starts to work in the Sprint immediately after Sprint Planning |  | SELECT … |  | Creates time waste
Daily Scrum | The Daily Scrum is held at the same time and place each day to reduce complexity. | The Daily Scrum is always 15-minute time-boxed event | 15 minutes | SELECT … | 0 | Decrease team discipline
|  | The Daily Scrum is used only for the Development Team to synchronize activities and create a plan for the next 24 hours. | Goal of the day | SELECT … |  | Unpredictable re-planning, double work, re-working and other associated wastes
|  | The Development Team is responsible for conducting the Daily Scrum. | Meeting owners | SELECT … |  | Dev team will use Daily Scrum as a status meeting for responsible person, for instance Scrum Master
|  | The Scrum Master has a courage to enforce the rule that only Development Team members participate in the Daily Scrum. |  | SELECT … |  | Reduce transparency and trust
|  | The Scrum Master is committed to teach the Development Team to keep the Daily Scrum within the 15-minute time-box and. | Scrum Master role on Daily Scrums | SELECT … |  | Ineffective Daily Scrum meeting
| The Daily Scrum is used by Development Team to optimize the probability that it will meet the Sprint Goal. | During the meeting, the Development Team members explain to each other: * What did I do yesterday that helped the Development Team meet the Sprint Goal? * What will I do today to help the Development Team meet the Sprint Goal? * Do I see any impediment that prevents me or the Development Team from meeting the Sprint Goal? | Three questions | SELECT … | 0 | Re-work, double work, unsynchronized activities, blockers and other wastes
|  | During the Daily Scrum the Development Team inspect how progress is trending toward completing the work in the Sprint Backlog. | Using burn-down chart or similar technique | SELECT … |  | Decrease ability of the DT to manage risks which turns into micromanagement from outside
|  | For detailed discussions, or to adapt, or replan, the rest of the Sprint’s work the Development Team or team members meet immediately after Scrum | Daily Scrum follow-ups | SELECT … |  | Non-reliable and sub-optimal development decisions, increased defects and bugs
|  | All team members has a courage to share their impediments. After Daily Scrum list of imediments is created | Impediments list | SELECT … |  | Failed Sprint
|  | When the progress is slow the Development Team is open to share it with Product Owner and re-negotiate the scope of the current Sprint | Re-negotiate | SELECT … |  | Overtimes and qulaity shortcuts
Sprint Review | The event takes place and attendants understand its purpose | This is a four-hour time-boxed meeting for one-month Sprints. | Timebox | SELECT … | 0 | Ineffective Sprint Review meeting
|  | A Sprint Review is held at the end of the Sprint to inspect the Increment and adapt the Product Backlog if needed | When and What? | SELECT … |  | Product risks and decrease trus between Scrum Team and stakeholders
|  | Attendees include the Scrum Team and key stakeholders invited by the Product Owner; | Participants | SELECT … |  | Decrease Dev Team motivation to participate Sprint Review
|  | This is an informal meeting, not a status meeting | Format | SELECT … |  | Decrease transparency and meeting value
|  | The Development Team prepares presentation of the Increment so that it helps to elicit feedback from stakeholders and foster collaboration. | How? | SELECT … |  | Decreased transparency and trust
| During the Sprint Review, the Scrum Team and stakeholders collaborate about what was done in the Sprint | The Product Owner explains what Product Backlog items have been “Done” and what has not been “Done” |  | SELECT … | 0 | Decreased transparency and trust
|  | The Development Team discusses what went well during the Sprint, what problems it ran into, and how those problems were solved |  | SELECT … |  | Decreased transparency and trust
|  | The Development Team demonstrates the work that it has “Done” and answers questions about the Increment |  | SELECT … |  | Decreased transparency and trust
|  | The Product Owner discusses the Product Backlog as it stands. He or she projects likely completion dates based on progress to date (if needed) |  | SELECT … |  | Decreased transparency and trust
|  | The PO is committed to transform feedback into PBIs |  | SELECT … |  | Decreased transparency and trust
| The entire group collaborates on what to do next, so that the Sprint Review provides valuable input to subsequent Sprint Planning; | The entire group (Stakeholders and Scrum Team) collaborates on what to do next, so that the Sprint Review provides valuable input to subsequent Sprint Planning; | Update Sprint Backlog and priorities | SELECT … | 0 | Frequent changes in priorities during the Sprint
|  | Review of how the marketplace or potential use of the product might have changed what is the most valuable thing to do next; and, | Refresh context of the Product | SELECT … |  | Frequent changes in priorities during the Sprint
|  | Review of the timeline, budget, potential capabilities, and marketplace for the next anticipated release of the product. | Next Release | SELECT … |  | Frequent changes in priorities during the Sprint
|  | Review how Team Impediments can be solved |  | SELECT … |  | Decreased transparency and trust
|  | Review team metrics and improvement progress |  | SELECT … |  | Decreased transparency and trust
Sprint Retrospective | Event takes place and attendants understand its purpose | This is a three-hour time-boxed meeting for one-month Sprints. For shorter Sprints, the event is usually shorter. | Timebox | SELECT … | 0 | Ineffective Sprint Retrospective meeting
|  | The Sprint Retrospective occurs after the Sprint Review and prior to the next Sprint Planning | When | SELECT … |  | Time wastes
|  | Scrum Team to inspect itself and create a plan for improvements to be enacted during the next Sprint | What | SELECT … |  | Decreased team perfromance in upcoming Sprint
|  | Every member of the Development Team shows-up on the Sprint Planning, including PO (if needed) and Scrum Master participates as a peer team member in the meeting from the accountability over the Scrum process. | Participants | SELECT … |  | Ineffective Sprint Retrospective meeting
|  | Scrum Team inspect how the last Sprint went with regards to people, relationships, process, and tools | Format | SELECT … |  | Decrease Dev Team motivation to participate Sprint Retrospective and use it for self-improving
| By the end of the Sprint Retrospective, the Scrum Team should have identified improvements that it will implement in the next Sprint. | Scrum Team identify and order the major items that went well and potential improvements; | Collaboration | SELECT … | 0 | Decrease ability to focus on the most important topics
|  | Scrum Team creates a plan for implementing improvements to the way the Scrum Team does its work. | Improvement Plan | SELECT … |  | Decreased commitment to act on improvement action points
|  | The Scrum Master encourages the Scrum Team to improve, within the Scrum process framework, its development process and practices to make it more effective and enjoyable for the next Sprint. | Scrum Master role on Retrospective | SELECT … |  | Decreased commitment to act on improvement action points
|  | During each Sprint Retrospective, the Scrum Team plans ways to increase product quality by adapting the definition of “Done” as appropriate. | Improving Definition of Done | SELECT … |  | Decreased product quality
|  | All Scrum Team memebres demonstrate responsibility to plan and implement improvements | Responsibility | SELECT … |  | Problems with responsibility

## Scrum Artifacts
Artifact | Rules | Practices | Comments | Assessment | Score | Risks When Not TRUE
Product Backlog | The Product Backlog is an ordered list of everything that might be needed in the product and is the single source of requirements for any changes to be made to the product. | Product Backlog priorities are always up-to-date | Follow the statements | SELECT … | 0 | Mess with priorities during the Sprint
|  | All features, functions, requirements, enhancements, and fixes that constitute the changes to be made to the product in future releases are listed in the single Product Backlog |  | SELECT … |  | Information loss and scatter, unclear priorities, increased defects
|  | A Product Backlog is never complete and contains product items for the next 6-8 Sprints |  | SELECT … |  | Increased strategical technical debt, risk to re-work design and architecture and release lippages
|  | Product Backlog can be easely transformed into Release Roadmap for the next 6-8 Sprints |  | SELECT … |  | Increased strategical technical debt, risk to re-work design and architecture and release lippages
|  | Can be easely understood by business stakeholders |  | SELECT … |  | Miscommunications, customer unsatisfaction, sub-optimal organizational decisions from the business stakeholders
| Product Backlog items have the attributes of a description, order, estimate and value. | Product Backlog items at the top of the list are testable and contain acceptance criteria for the next Sprint. | Follow the statements | SELECT … | 0 | Re-works, increased defects and bugs
|  | Entire Product Backlog is estimated. It can be used to forecast completion dates of the strategic part |  | SELECT … |  | Inability to track project risks and manage customer expectation
|  | Every item described the way that business understand its value, and this value was shared with the team so everyone clearly understands business purpose and priority of the story |  | SELECT … |  | Miscommunications, customer unsatisfaction, sub-optimal organizational decisions from the business stakeholders
|  | Items at the top of the list are sized right. Any one item can reasonably be “Done” within the Sprint time-box. |  | SELECT … |  | Deliver unusable outcomes by the end of the Sprint
|  | Development Team understands impact of PBI not being delivered on time (e.g. lost business opportunities or deadline for some regulatory changes) |  | SELECT … |  | Creates overtimes, reduces trust, increased micromanagement from the customer side
| Product Backlog refinement is the act of adding detail, estimates, and order to items in the Product Backlog. | Entire Scrum Team has regular PBR meetings on weekly basis to collaborate on the details of Product Backlog items | Follow the statements | SELECT … | 0 | Decreased Product Backlog transparency, many unclear items, overtimes, re-works and quality problems
|  | Refinement usually consumes no more than 10% of the capacity of the Development Team. |  | SELECT … |  | Reduction in produced value
|  | PBR meetings are well facilitated and time-boxed with clear agenda |  | SELECT … |  | Dev Team motivation to participate PBR meetings
|  | The Development Team is responsible for all estimates in the Product Backlog and during PBR meetings team is updating estimates |  | SELECT … |  | Unreliable estimates, unrealistic expectations, decreased team morale
|  | The Product Owner is helping the Development Team to understand and select trade-offs during estimation process |  | SELECT … |  | Sub-optimal decisions from Dev Team and decreased trust
| Product Backlog items that can be “Done” by the Development Team within one Sprint are deemed “Ready” for selection in a Sprint Planning. | Product Backlog items has "Ready" for development status | Follow the statements | SELECT … | 0 | Unpredictable estimates, delays and conflicts between PO and Dev Team during the Sprint
|  | The team is always has enough "Ready" for development items before the next Sprint Planning |  | SELECT … |  | Increase uncertainty
|  | PBR process also includes a time for Development Team to accomplish reasonable technical investigations in case when they are not able to provide good estimate for top priority items |  | SELECT … |  | Unpredictable estimates, delays and conflicts between PO and Dev Team during the Sprint
|  | Scrum Team is splitting Product Backlog items when it is too big to accomplish according to DoD within the next Sprint |  | SELECT … |  | Reduction in produced value
|  | For top priority items the Scrum Team is providing well refined acceptance criteria and other requirements approved by the Product Owner |  | SELECT … |  | Re-works, increased defects and bugs
Sprint Backlog | The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. | Only Development Team can create or change tasks in the Sprint Backlog | Follow the statements | SELECT … | 0 | Reduces team responsibility over results
|  | The Sprint Backlog is a plan with enough detail that changes in progress can be understood in the Daily Scrum |  | SELECT … |  | Increases miscommunications and decreases transparency
|  | Sprint Backlog containins all the tasks to turn at least one PBI into usable and releasable Increment according to DoD |  | SELECT … |  | Decreases predictability of the overall project forecasts
|  | Sprint Backlog containins tasks from the previous Retrospective meeting |  | SELECT … |  | Decreases quality and team productivity
|  | Sprint Backlog contains tasks for analysis and PBR activities |  | SELECT … |  | Unrealistic forecasts and plans
| The Development Team modifies the Sprint Backlog throughout the Sprint, and the Sprint Backlog emerges during the Sprint. | Any Development Team member can add, delete or change the Sprint Backlog. Update work remaining as more is known, as items are worked | Follow the statements | SELECT … | 0 | Decreases team self-organization and responsibility over delivery
|  | Development Team has a consistent agreement of how to estimate efforts: pure efforts or including meetings, possible impediments, delays, etc |  | SELECT … |  | Decreases reliability of estimates
|  | Development Team members sign up for tasks, they aren't assigned by Scrum Master or Manager |  | SELECT … |  | Decreases team self-organization and responsibility over delivery
|  | Estimated work remaining is updated daily |  | SELECT … |  | Decreases transparency of the progress, increases the level of external micromanagement
|  | The Development Team tracks the total work remaining at least for every Daily Scrum to project the likelihood of achieving the Sprint Goal. |  | SELECT … |  | Decreases ability to make reliable decisions and manage delivery risks
Increment | At the end of a Sprint, the new Increment must be “Done,” which means it must be in useable condition and meet the Scrum Team’s definition of “Done.” | DoD checklist should consist of valuable activities required to produce high potentally releasable increment. | Follow the statements | SELECT … | 0 | Unreleasbale and unuseable Sprint results
|  | Scrum Teams and Stakeholders similarily understand what “Done” means. |  | SELECT … |  | Miscommunications, customer unsatisfaction, sub-optimal organizational decisions from the business stakeholders
|  | DoD is not static and expanded over a time. Sometimes inspected and adapted during Sprint Retrospective meeting |  | SELECT … |  | Decreases quality and team productivity
|  | The definition of “done” is used to assess when work is complete on the product Increment. |  | SELECT … |  | Decreases Increment transparency and ability to provide reliable project forecasts
|  | The definition of "done" for an increment includes conventions, standards or guidelines of the development organization |  | SELECT … |  | Can significantly affect initial estimates or the dev team velocity, creates risk to fail customer service, expected delivery
| Development Teams deliver an Increment of product functionality every Sprint. | Increment is useable, so a Product Owner may choose to immediately release it | Follow the statements | SELECT … | 0 | Decrease ability to manage project forecasts reliably
|  | Each Increment is additive to all prior Increments and thoroughly tested, ensuring that all Increments work together. |  | SELECT … |  | Decrease quality and increase future time to manage technical debt
|  | Development Team is committed to remove all the impediments to achieve releasable and usable state by the end of the Sprint |  | SELECT … |  | Risks to fail Increment
|  | Multiple teams works in the same Sprint and achieve integrated Increment |  | SELECT … |  | Risks to fail Increment
|  | Business Stakeholders are able to assess Product Increment value by the end of the Sprint and provide feedback on the Product |  | SELECT … |  | Decrease trust and transparency

## Data
FALSE | 0
NOT SURE | 0
TRUE | 1
SELECT … | 0